## START HERE
EEE4022S ¦ Laboratory Data Logger
26 October 2026 • Rev0 as-built • Enter only actual observations in blue-field sheets; formulas derive output metrics.
Step | Activity | Expected evidence | Gate / instruction
1 | Stationary geometry & windings | Gap, runout, resistance and temperature | Do not rotate unless mechanical assembly inspected and approved
2 | Open-circuit generator tests | Actual rpm, frequency, RMS AB/BC/CA, CSV | Motor disconnected from inverter; safe differential probing
3 | Controller / driver commissioning | PWM, shutdown, current feedback, encoder | Keep DC link unpowered until specific interfaces and protections verified
4 | Powered motor runs (conditional) | Current, bus power, torque, shaft speed | Only after safety commissioning and appropriate torque measurement
5 | Review and export | Raw files, uncertainties, comparisons | Blank cells = not measured; never replace with predictions
Legend | Blue-tinted input columns | Enter measured values and test identifiers | Grey/green outputs are derived from formulas

## Geometry
1 ¦ Physical Geometry & Winding Checks
Measure minimum magnet-face–PCB distance at several positions; record runout and uncertainties.
Date/time | Rotor angle (deg) | Gap (mm) | Gauge uncertainty (mm) | Runout / note | Operator | Metric | Value
TODAY | 0 | 4 |  |  |  | Min gap (mm) | 4
| 45 | 4 |  |  |  | Max gap (mm) | 4
| 90 | 4 |  |  |  | Mean gap (mm) | 4
| 135 | 4
| 180 | 4
| 225 | 4
| 270 | 4
| 315 | 4

## Windings
2 ¦ Static Electrical Measurements
Star connection: line-line resistance generally spans two phases; record exact terminals and lead-compensation method.
Measurement | Terminals | Reading | Unit | Frequency (Hz) | Ambient °C | Lead offset / method | Instrument | Notes
Line resistance | AB | 3.83 | ohm
Line resistance | BC | 3.81 | ohm
Line resistance | CA | 3.83 | ohm
Phase resistance | A–star | 1.93 | ohm
Phase resistance | B–star | 1.91 | ohm
Phase resistance | C–star | 1.91 | ohm
Inductance | AB |  | uH | 1000
Inductance | BC |  | uH | 1000
Inductance | CA |  | uH | 1000
Single board R | A | 0.46 | ohm
| A | 36.0867 | uH | phase inductances
| B | 35.9419 | uH
| C | 36.0562 | uH

## Back EMF
3 ¦ Open-Circuit Back-EMF
Blue fields: measured speed, voltage, frequency and waveform ID. Prediction is Case C at 4 mm; no assumed observations.
Test ID | Cmd rpm | Pair | Repeat | Actual rpm | V LL RMS (mV) | Freq measured (Hz) | Freq expected (Hz) | Case C prediction @cmd (mV) | Prediction @actual (mV) | Deviation (%) | K inferred (mN m/A) | CSV filename | Notes
BE50_AB_01 | 50 | AB | 1 |  |  |  |  | 48.4
BE50_AB_02 | 50 | AB | 2 |  |  |  |  | 48.4
BE50_AB_03 | 50 | AB | 3 |  |  |  |  | 48.4
BE50_BC_01 | 50 | BC | 1 |  |  |  |  | 48.4
BE50_BC_02 | 50 | BC | 2 |  |  |  |  | 48.4
BE50_BC_03 | 50 | BC | 3 |  |  |  |  | 48.4
BE50_CA_01 | 50 | CA | 1 |  |  |  |  | 48.4
BE50_CA_02 | 50 | CA | 2 |  |  |  |  | 48.4
BE50_CA_03 | 50 | CA | 3 |  |  |  |  | 48.4
BE100_AB_01 | 100 | AB | 1 |  |  |  |  | 96.9
BE100_AB_02 | 100 | AB | 2 |  |  |  |  | 96.9
BE100_AB_03 | 100 | AB | 3 |  |  |  |  | 96.9
BE100_BC_01 | 100 | BC | 1 |  |  |  |  | 96.9
BE100_BC_02 | 100 | BC | 2 |  |  |  |  | 96.9
BE100_BC_03 | 100 | BC | 3 |  |  |  |  | 96.9
BE100_CA_01 | 100 | CA | 1 |  |  |  |  | 96.9
BE100_CA_02 | 100 | CA | 2 |  |  |  |  | 96.9
BE100_CA_03 | 100 | CA | 3 |  |  |  |  | 96.9
BE150_AB_01 | 150 | AB | 1 |  |  |  |  | 145.3
BE150_AB_02 | 150 | AB | 2 |  |  |  |  | 145.3
BE150_AB_03 | 150 | AB | 3 |  |  |  |  | 145.3
BE150_BC_01 | 150 | BC | 1 |  |  |  |  | 145.3
BE150_BC_02 | 150 | BC | 2 |  |  |  |  | 145.3
BE150_BC_03 | 150 | BC | 3 |  |  |  |  | 145.3
BE150_CA_01 | 150 | CA | 1 |  |  |  |  | 145.3
BE150_CA_02 | 150 | CA | 2 |  |  |  |  | 145.3
BE150_CA_03 | 150 | CA | 3 |  |  |  |  | 145.3

## Commissioning
4 ¦ Drive-Interface Commissioning Log
Gate-driver work requires verified pinout, current sensing, independent fault shutdown and mechanical approval before energising the motor.
Check ID | Subsystem | Evidence / test | Status | Measured value | Instrument / file | Owner | Safety note
C01 | Mechanics | Rotor stable, guard and retention approved | Not checked |  |  |  | No rotation without approval
C02 | DC-link | Verified voltage range, discharge and polarity | Not checked |  |  |  | Check de-energised capacitors
C03 | Aux supply | Correct voltage, isolation and current demand | Not checked |  |  |  | 15 V label not PWM input
C04 | PWM | All six outputs, polarity, dead time, disabled state | Not checked |  |  |  | STM32 only first
C05 | Gate inputs | GDC-7A6S1 pin map and 3.3V compatibility | Not checked |  |  |  | Do not infer from another board
C06 | Protection | Hardware shutdown / emergency stop validated | Not checked |  |  |  | Bench supply limit is insufficient
C07 | Phase current | ADC scaling, bias, polarity and calibration | Not checked |  |  |  | Low current accuracy essential
C08 | Encoder | Eight pole pairs, angle, direction, alignment | Not checked |  |  |  | No open-loop forced startup on unsafe rig
C09 | Power stage | Approved dummy-load low-energy commissioning | Not checked |  |  |  | Motor disconnected
C10 | Motor | Formal approval for controlled powered test | Not checked |  |  |  | Required before data-taking

## Motor Runs
5 ¦ Loaded / No-Load Motor Test Log
Use only after full commissioning. Torque must be within the verified useful sensor range. P_DC is average bus power; system efficiency includes inverter.
Test ID | Mode | Target rpm | Actual rpm | Iq peak (A) | I phase RMS (A) | V DC (V) | I DC mean (A) | P DC measured (W) | Torque shaft (mN m) | P shaft (W) | Efficiency (%) | P DC est (W) | Stator temp °C | Ambient °C | Load description | Instrument / raw file | Valid? | Notes
M001
M002
M003
M004
M005
M006
M007
M008
M009
M010
M011
M012
M013
M014
M015
M016
M017
M018
M019
M020
M021
M022
M023
M024
M025
M026
M027
M028
M029
M030

## Summary
6 ¦ Session Summary
Calculated summaries reflect recorded data only. Predicted values must not be entered as measurements.
Metric | Calculated / recorded | Meaning | Notes
Recorded back-EMF rows | 0 | Number of rows with measured RMS and shaft speed | 3 phase pairs × 3 proposed speeds × 3 repetitions
Mean K inferred (mN m/A) |  | Simple mean from individual valid numerical entries | Interpret only with instrument uncertainty and actual gap
Completed motor runs | 0 | Number of motor points with rpm and torque | Not proof that torque sensor is adequately ranged
Maximum recorded shaft power (W) |  | From recorded torque and speed | Only if measured torque is credible
Average available system efficiency (%) |  | From measured DC input power and shaft power | Excludes rows without both measurements
Nominal reference K (mN m/A) | 18.534 | Simulation: 1 mm nominal Rev0 | Not a measured value
As-built Case C K (mN m/A) | 7.554 | Simulation: 4 mm as-built Rev0 | Model-derived, sheet-current corrected
As-built predicted ELL at 100 rpm (mV) | 96.9 | Simulation | Model-derived